## Team
Initials | First | Last | Email | GitHub Username
no | Nestor | Ouranitsas | nouranit@stevens.edu | nestouranitsas
dc | Dakota | crouchelli | dcrouche@stevens.edu | northorsouth
|  |  | GitHub Repository: | https://github.com/northorsouth/ssw555tm022018Spring
|  |  | Communication Line: | Google hangouts/phone
|  |  | Programming Language: | Python 3
|  |  | Database: | sqLite3

## Backlog
Sprint | Story ID | Story Name | Owner | Status
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date | DC | done
US02 | Birth before marriage | Birth should occur before marriage of an individual | DC | done
US03 | Birth before death | Birth should occur before death of an individual | NO | done
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage | NO | done
US05 | Marriage before death | Marriage should occur before death of either spouse | DC | done
US16 | Male last names | All male members of a family should have the same last name | NO | done
US18 | Siblings should not marry | Siblings should not marry one another | DC | done
US21 | Correct gender for role | Husband in family should be male and wife in family should be female | NO | done
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique | DC
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US29 | List deceased | List all deceased individuals in a GEDCOM file | NO
US30 | List living married | List all living married people in a GEDCOM file | NO
US32 | List multiple births | List all multiple births in a GEDCOM file | DC
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2018-02-12 | 16 |  | 0
2018-02-26 | 12 | 4 | 80 | 255 | 18.8235
2018-03-14 | 8 | 4 | 150 | 70 | 60

## Sprint1
Story ID | Story Name | Owner | Status | Est Size (LOC) | Est Time (mins) | Act Size (LOC) | Act Time (mins) | Completed
T0.0 | develop date conversion method to be used in stories for this sprint | DC/NO | complete | 35 | 45 | 15 | 60 | yes
T0.1 | begin developing automated testing suite | DC/NO | complete | 75 | 75 | 15 | 30 | yes
US01 | Dates before current date | DC | complete | 10 | 25 | 10 | 15 | yes
US02 | Birth before marriage | DC | complete | 10 | 25 | 30 | 120 | yes
US03 | Birth before death | NO | complete | 65 | 25 | 5 | 15 | yes
US04 | Marriage before divorce | NO | complete | 65 | 25 | 5 | 15 | yes
Review Results
Keep doing:
- pair programming/screen shares
- Test Driven Development
- Use checks in database code for User stories
- weekly meetings
- after class catch up
Avoid:
- concurrent git commits
- avoid multiple instances of radical refactoring

## Sprint2
Story ID | Story Name | Owner | Status | Est Size (LOC) | Est Time (mins) | Act Size (LOC) | Act Time (mins) | Completed
US05 | Marriage before death | DC | pending | 10 | 45 | 15 | 10 | yes
US18 | Siblings should not marry | DC | pending | 25 | 120 | 20 | 20 | yes
US16 | Male last names | NO | pending | 30 | 35 | 20 | 25 | yes
US21 | Correct gender for role | NO | pending | 35 | 50 | 15 | 15 | yes
Review Results
Keep doing:
- refactor when necssary
- Test Driven Development
- create new classes for test when applicable
- weekly meetings
- after class catch up
Avoid:
- large test classes
- anaomly checks in database code for User Stories
-multiple instances of the same code

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US22 | Unique IDs | DC | pending | 5 | 10 | 6 | 20 | yes
US29 | List deceased | NO | pending | 20 | 35 | 10 | 30 | yes
US30 | List living married | NO | pending | 20 | 35 | 25 | 40 | yes
US32 | List multiple births | DC | pending | 20 | 35 | ~ | ~30 | no
Review Results
Keep doing:
- refactor when necessary
- TDD
- create new classes for test cases when applicable
- weekly meetings
- after class catch up
Avoid:
- dramatic refactoring
- wearing selves out trying to solve a problem

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US23 | Unique name and birth | NO | incomplete | 20 | 15
US33 | List orphans | NO | incomplete | 35 | 30
US34 | List large age differences | DC | incomplete | 25 | 25
US28 | order siublings by age | DC | incomplete | 15 | 15

## Stories
Story ID | Story Name | Story Description | story points
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date | 1
US02 | Birth before marriage | Birth should occur before marriage of an individual | 1
US03 | Birth before death | Birth should occur before death of an individual | 1
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage | 1
US05 | Marriage before death | Marriage should occur before death of either spouse | 1
US06 | Divorce before death | Divorce can only occur before death of both spouses | 1
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people | 1
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce) | 2
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father | 2
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old) | 1
US11 | No bigamy | Marriage should not occur during marriage to another spouse | 15
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children | 2
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day) | 2
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time | 2
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family | 1
US16 | Male last names | All male members of a family should have the same last name | 1
US17 | No marriages to descendants | Parents should not marry any of their descendants | 3
US18 | Siblings should not marry | Siblings should not marry one another | 2
US19 | First cousins should not marry | First cousins should not marry one another | 3
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews | 3
US21 | Correct gender for role | Husband in family should be male and wife in family should be female | 1
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique | 1
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file | 1
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file | 1
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family | 1
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent. | 1
US27 | Include individual ages | Include person's current age when listing individuals | 2
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first | 1
US29 | List deceased | List all deceased individuals in a GEDCOM file | 1
US30 | List living married | List all living married people in a GEDCOM file | 1
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file | 2
US32 | List multiple births | List all multiple births in a GEDCOM file | 2
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file | 2
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse | 2
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days | 2
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days | 2
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days | 3
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days | 2
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days | 2
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors | 2
US41 | Include partial dates | Accept and use dates without days or without days and months | 3
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate) | 2